## Confidence report
Epic | Epic status | # | Title | Assigned | % done | Conf. | Comment | TL Action Item | Comment (delete)
PS-6814 (Quotation Process & RFQ) | In Progress | PS-8114 | As Agent I want to be able to make one more round of negotiates on Request for Quote that was Ready | Dmitriy Aseev | 70 | 0 |  | Myself | test test
|  | PS-8021 | As Buyer I'm expecting that RfQ will have close status right after I place and order from it. | Anastasia Chistokhvalova | 80 | 0 |  | Myself
|  | PS-8008 | As Buyer I want to be redirected to the warning page if I'm Editing items on the RfQ and trying to switch to another one. | Anton Smarovydlo | 70 | 0 |  | Myself
|  | PS-7898 | As Agent I want to view RfQ | Anastasia Chistokhvalova | 100 | 10 |  | Myself
|  | PS-7517 | As Agent I should find Agent account page after I login | Anastasia Chistokhvalova | 100 | 10 |  | Myself
|  | PS-6960 | As Buyer I should not be able to place Order with RfQ that is not valid already | Anastasia Chistokhvalova | 80 | 0 |  | Myself
|  | PS-6959 | As Buyer I want to Submit Order from RfQ that has "Ready" status | Anastasia Chistokhvalova | 80 | 0 |  | Myself
|  | PS-6958 | As Buyer I want to be able to make one more round of negotiates on Request for Quote that was Ready | Anton Smarovydlo | 70 | 0 |  | Myself
|  | PS-6816 | As Agent I should be able to Create RfQ for Buyer | Dmitriy Aseev | 70 | 0 |  | Myself
|  | PS-6815 | As Agent I should be able to set on Edit RFQ page Life Time for RfQ | Anastasia Chistokhvalova | 80 | 0 |  | Myself
|  | PS-6802 | As Agent I should get to the Warning page if I want to switch from Editing RfQ to another one. | Andrew Chekanov | 100 | 10 |  | Myself
|  | PS-6801 | As Agent I should find list with all my quotes in Agent RfQ list page | Anastasia Chistokhvalova | 100 | 10 |  | Myself
|  | PS-6800 | As Agent I should get to the Warning page if I want to switch from RFQ while I'm editing items | Anastasia Chistokhvalova | 100 | 10 |  | Myself
|  | PS-6798 | As Agent I should be able to find Agent RfQ widget on top of the screen | Anastasia Chistokhvalova | 80 | 0 |  | Myself
|  | PS-6795 | Enabler: Create new modules and extend DB schema. | Anastasia Chistokhvalova | 100 | 10 |  | Myself
|  | PS-6793 | As Agent I should be able to overwrite prices on Edit RfQ page | Anastasia Chistokhvalova | 80 | 0 |  | Myself
|  | PS-6792 | As Agent I should be able to Edit RfQ | Anastasia Chistokhvalova | 80 | 0 |  | Myself
|  | PS-6791 | As Agent I should be able to Edit items in RfQ | Anastasia Chistokhvalova | 80 | 0 |  | Myself
|  | PS-6790 | As Buyer I should be able to manage RfQ in my Customer account | Anastasia Chistokhvalova | 100 | 10 |  | Myself
|  | PS-6752 | As Buyer I should find in my Customer Account list with all my quotes | Anastasia Chistokhvalova | 100 | 10 |  | Myself
|  | PS-6751 | As Buyer I should be able to create a Request for Quote (RFQ) from my cart page | Anastasia Chistokhvalova | 80 | 0 |  | Myself
PS-7272 (Add Total to shopping list) | In Progress | PS-7347 | As Buyer I want to find Subtotal on the shopping list View and Edit page | Anastasia Chistokhvalova | 80 | 0 |  | Myself | test test